## Sheet1
Topic | Task | Responsible | Comments
|  |  |  | 2019-11-26 | 2019-11-27 | 2019-12-03 | 2019-12-04 | 2019-12-07 | 2019-12-01 | 2019-12-02 | 2019-12-03 | 2019-12-04 | 2019-12-05 | 2019-12-08 | 2019-12-09 | 2019-12-10 | 2019-12-11 | 2019-12-12
Step 2 | Project development workplan (Gantt chart) | Together
| Software Requirement Specifications (SRS) | Together
| Report on how reqs were gathered | Ali
| Feasibility report | Haseeb
| Function points analysis (FPA) | Haseeb
| Software process model | Aiza
Step 3 | Use case diagram | Ali
| Textual description of each use case | Haseeb
| Activity diagram for two use cases | Aiza
| Class diagram | Aiza
| Sequence diagram | Aiza
Step 4 | Back-end code | Ali
| Front-end code | Ali
| Test plan and test cases | Aiza, Ali
| Do testing | Together
| Write test results document | Aiza, Ali
Deliverable 1
Deliverable 2