## Sheet1
Topic | Task | Responsible | Comments
|  |  |  | 2019-11-26 | 2019-11-27 | 2019-12-03 | 2019-12-04 | 2019-12-07 | 2019-12-08 | 2019-12-09 | 2019-12-10 | 2019-12-11 | 2019-12-12
Step 2 | Project development workplan (Gantt chart) | Together | bar: 2019-11-26
| Software Requirement Specifications (SRS) | Together | bar: 2019-11-26
| Report on how reqs were gathered | Ali | bar: 2019-11-27
| Feasibility study | Haseeb | bar: 2019-12-03
| Function points analysis (FPA) | Haseeb | bar: 2019-12-03
| Software process model document | Aiza | bar: 2019-12-04
Step 3 | Use case diagram | Ali | bar: 2019-12-04
| Textual description of each use case | Haseeb | bar: 2019-12-04 to 2019-12-07
| Activity diagram for two use cases | Aiza | bar: 2019-12-04 to 2019-12-07
| Class diagram | Aiza | bar: 2019-12-08
| Sequence diagram | Ali | bar: 2019-12-08
Step 4 | Back-end code | Ali | bar: 2019-12-08 to 2019-12-09
| Front-end code | Ali | bar: 2019-12-09 to 2019-12-10
| Test plan and test cases | Aiza, Ali | bar: 2019-12-10
| Do testing | Together | bar: 2019-12-11 to 2019-12-12
| Write test results document | Aiza, Ali
Deliverable 1
Deliverable 2